## Spent_Hours
Period | Cumulative_Spent_Hours
2012-01-06 | 2101.6596
2012-01-13 | 3828.4109
2012-01-20 | 5555.1623
2012-01-27
2012-02-03
2012-02-10
2012-02-17
2012-02-24
2012-03-02
2012-03-09
2012-03-16
2012-03-23
2012-03-30
2012-04-06
2012-04-13
2012-04-20
2012-04-27
2012-05-04
2012-05-11
2012-05-18
2012-05-25
2012-06-01
2012-06-08
2012-06-15
2012-06-22
2012-06-29
2012-07-06
2012-07-13
2012-07-20
2012-07-27
2012-08-03
2012-08-10
2012-08-17
2012-08-24
2012-08-31
2012-09-07
2012-09-14
2012-09-21
2012-09-28
2012-10-05
2012-10-12
2012-10-19
2012-10-26
2012-11-02
2012-11-09
2012-11-16
2012-11-23
2012-11-30
2012-12-07
2012-12-14
2012-12-21
2012-12-28
2013-01-04
2013-01-11
2013-01-18
2013-01-25
2013-02-01
2013-02-08
2013-02-15
2013-02-22

## Actual
[6 empty] | 2012-01-20 | Earned Value | Current | Current | Budget
1 | 2 | 3 | 4 | 5 | 6 | ID | Commodity_ID | WBS | Activity Name | Quantities At Completion | PR | budget(H) | 2012-01-13 | 2012-01-20 | 2012-01-27 | 2012-02-03 | 2012-02-10 | 2012-02-17 | 2012-02-24 | 2012-03-02 | 2012-03-09 | 2012-03-16 | 2012-03-23 | 2012-03-30 | 2012-04-06 | 2012-04-13 | 2012-04-20 | 2012-04-27 | 2012-05-04 | 2012-05-11 | 2012-05-18 | 2012-05-25 | 2012-06-01 | 2012-06-08 | 2012-06-15 | 2012-06-22 | 2012-06-29 | 2012-07-06 | 2012-07-13 | 2012-07-20 | 2012-07-27 | 2012-08-03 | 2012-08-10 | 2012-08-17 | 2012-08-24 | 2012-08-31 | 2012-09-07 | 2012-09-14 | 2012-09-21 | 2012-09-28 | 2012-10-05 | 2012-10-12 | 2012-10-19 | 2012-10-26 | 2012-11-02 | 2012-11-09 | 2012-11-16 | 2012-11-23 | 2012-11-30 | 2012-12-07 | 2012-12-14 | 2012-12-21 | 2012-12-28 | 2013-01-04 | 2013-01-11 | 2013-01-18 | 2013-01-25 | 2013-02-01 | 2013-02-08 | 2013-02-15 | 2013-02-22 | 0
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-02 | CIVIL | 1 |  | Baseline.06.02.01.01.01 | Foundation Civil Works | 253 | 0.167 | 1514.9701 | 5% | 10% | 15%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-02 | MECHANICAL | 2 | MC1 | Baseline.06.02.01.01.03 | EREC.OF ASSEMBLED MACHINERY | 15000 | 39.84 | 376.506 | 10% | 15% | 20%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-02 | PIPING | 3 | IN | Baseline.06.02.01.01.04 | INSUL.OF HOT & TRACED EQUIPM. | 8000 | 0.8 | 10000 | 25% | 30% | 35%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-02 | PIPING | 4 | FC | Baseline.06.02.01.01.04 | FIN.COAT FOR MACH./MEC.LIFTING | 60 | 3.5 | 17.1429 | 30% | 35% | 40%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-03 | CIVIL | 5 | CW | Baseline.06.02.01.02.01 | Foundation Civil Works | 2000 | 0.167 | 11976.0479 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-03 | MECHANICAL | 6 | MC1 | Baseline.06.02.01.02.03 | EREC.OF ASSEMBLED MACHINERY | 50000 | 26.56 | 1882.5301 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-03 | PIPING | 7 | IN | Baseline.06.02.01.02.04 | INSUL.OF HOT & TRACED EQUIPM. | 50 | 0.8 | 62.5 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-03 | PIPING | 8 | FC | Baseline.06.02.01.02.04 | FIN.COAT FOR MACH./MEC.LIFTING | 60 | 3.5 | 17.1429 | 5% | 10% | 15%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-04 | CIVIL | 9 | CW | Baseline.06.02.01.03.01 | Foundation Civil Works | 200 | 0.167 | 1197.6048 | 10% | 15% | 20%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-04 | MECHANICAL | 10 | MC1 | Baseline.06.02.01.03.03 | EREC.OF ASSEMBLED MACHINERY | 50000 | 26.56 | 1882.5301 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-04 | PIPING | 11 | IN | Baseline.06.02.01.03.04 | INSUL.OF HOT & TRACED EQUIPM. | 500 | 0.8 | 625 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-04 | PIPING | 12 | FC | Baseline.06.02.01.03.04 | FIN.COAT FOR MACH./MEC.LIFTING | 400 | 3.5 | 114.2857 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-05 | CIVIL | 13 | CW | Baseline.06.02.01.04.01 | Foundation Civil Works | 200 | 0.167 | 1197.6048 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-05 | MECHANICAL | 14 | MC1 | Baseline.06.02.01.04.03 | EREC.OF ASSEMBLED MACHINERY | 300 | 26.56 | 11.2952 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-05 | PIPING | 15 | IN | Baseline.06.02.01.04.04 | INSUL.OF HOT & TRACED EQUIPM. | 40 | 0.8 | 50 |  | 5% | 10%
Project | CONSTRUCTION | PROCESS | MAIN PUMPS AREA | PUMP 01-PR-05 | PIPING | 16 | FC | Baseline.06.02.01.04.04 | FIN.COAT FOR MACH./MEC.LIFTING | 50 | 3.5 | 14.2857 |  | 5% | 10%
Project | CONSTRUCTION | GENERAL | GENERAL AREA | CIVIL |  | 17 | TS | Baseline.06.01.01.01 | Top soil removal | 9000 | 30 | 300 |  | 5% | 10%
Project | CONSTRUCTION | GENERAL | GENERAL AREA | CIVIL |  | 18 | GE | Baseline.06.01.01.01 | GENERAL EXCAVATIONS | 50000 | 12.33 | 4055.15 |  | 5% | 10%
Project | CONSTRUCTION | GENERAL | GENERAL AREA | CIVIL |  | 19 | GB | Baseline.06.01.01.01 | General backfil. of area/roads | 25000 | 8.36 | 2990.4306 |  | 5% | 10%
Project | CONSTRUCTION | UTILITIES |  |  |  | 20 | GB | Baseline.06.03 | General backfil. of area/roads | 15000 | 8.36 | 1794.2584 |  | 15%
Project | CONSTRUCTION | TANK FARM |  |  |  | 21 | GB | Baseline.06.04 | General backfil. of area/roads | 205622 | 8.36 | 24595.933

## Dashboard
Time | Planned | Earned | Planned_Budget | Actual_Budget | Time | Planned | Actual | Commodity_ID | Commodity | Time | Planned | Actual | Commodity_ID | Commodity | Time | Planned | Actual | Commodity_ID | Commodity
2012-01-06 | 0% | #N/A | 1514.9701 | 1514.9701 | 2012-01-06 | 0 | #N/A | TS | Top soil removal | 2012-01-06 | 0 | #N/A | CW | Foundation Civil Works | 2012-01-06 | 0 | #N/A | GE | GENERAL EXCAVATIONS |  |  | Sample Project |  |  |  |  | CW | Foundation Civil Works | M3
2012-01-13 | 0% | #N/A |  |  | 2012-01-13 | 0 | #N/A |  |  | 2012-01-13 | 0 | #N/A |  |  | 2012-01-13 | 0 | #N/A | [6 empty] | Dashboard Report | 2012-01-20 |  | MC1 | EREC.OF ASSEMBLED MACHINERY | KG
2012-01-20 | 0% | #N/A |  |  | 2012-01-20 | 0 | #N/A |  |  | 2012-01-20 | 0 | #N/A |  |  | 2012-01-20 | 0 | #N/A | [9 empty] | FC | FIN.COAT FOR MACH./MEC.LIFTING | M2
2012-01-27 | 0% | #N/A |  |  | 2012-01-27 | 0 | #N/A |  |  | 2012-01-27 | 0 | #N/A |  |  | 2012-01-27 | 0 | #N/A
2012-02-03 | 0% | #N/A |  |  | 2012-02-03 | 0 | #N/A |  |  | 2012-02-03 | 0 | #N/A |  |  | 2012-02-03 | 0 | #N/A | [9 empty] | TS | Top soil removal | M2
2012-02-10 | 0% | #N/A |  |  | 2012-02-10 | 0 | #N/A |  |  | 2012-02-10 | 0 | #N/A |  |  | 2012-02-10 | 0 | #N/A | [9 empty] | GE | GENERAL EXCAVATIONS | M3
2012-02-17 | 0% | #N/A |  |  | 2012-02-17 | 0 | #N/A |  |  | 2012-02-17 | 0 | #N/A |  |  | 2012-02-17 | 0 | #N/A | [9 empty] | GB | General backfil. of area/roads | M3
2012-02-24 | 0% | #N/A |  |  | 2012-02-24 | 0 | #N/A |  |  | 2012-02-24 | 0 | #N/A |  |  | 2012-02-24 | 0 | #N/A | [9 empty] | 0 | 0 | 0
2012-03-02 | 0% | #N/A |  |  | 2012-03-02 | 0 | #N/A |  |  | 2012-03-02 | 0 | #N/A |  |  | 2012-03-02 | 0 | #N/A | [9 empty] | 0
2012-03-09 | 0% | #N/A |  |  | 2012-03-09 | 0 | #N/A |  |  | 2012-03-09 | 0 | #N/A |  |  | 2012-03-09 | 0 | #N/A | [9 empty] | 0
2012-03-16 | 0% | #N/A |  |  | 2012-03-16 | 0 | #N/A |  |  | 2012-03-16 | 0 | #N/A |  |  | 2012-03-16 | 0 | #N/A | [9 empty] | 0
2012-03-23 | 0% | #N/A |  |  | 2012-03-23 | 0 | #N/A |  |  | 2012-03-23 | 0 | #N/A |  |  | 2012-03-23 | 0 | #N/A | [9 empty] | 0
2012-03-30 | 0% | #N/A |  |  | 2012-03-30 | 0 | #N/A |  |  | 2012-03-30 | 0 | #N/A |  |  | 2012-03-30 | 0 | #N/A | [9 empty] | 0
2012-04-06 | 0% | #N/A |  |  | 2012-04-06 | 0 | #N/A |  |  | 2012-04-06 | 0 | #N/A |  |  | 2012-04-06 | 0 | #N/A | [9 empty] | 0
2012-04-13 | 0% | #N/A |  |  | 2012-04-13 | 0 | #N/A |  |  | 2012-04-13 | 0 | #N/A |  |  | 2012-04-13 | 0 | #N/A | [9 empty] | 0
2012-04-20 | 0% | #N/A |  |  | 2012-04-20 | 0 | #N/A |  |  | 2012-04-20 | 0 | #N/A |  |  | 2012-04-20 | 0 | #N/A | [9 empty] | 0
2012-04-27 | 0% | #N/A |  |  | 2012-04-27 | 0 | #N/A |  |  | 2012-04-27 | 0 | #N/A |  |  | 2012-04-27 | 0 | #N/A | [9 empty] | 0
2012-05-04 | 0% | #N/A |  |  | 2012-05-04 | 0 | #N/A |  |  | 2012-05-04 | 0 | #N/A |  |  | 2012-05-04 | 0 | #N/A
2012-05-11 | 0% | #N/A |  |  | 2012-05-11 | 0 | #N/A |  |  | 2012-05-11 | 0 | #N/A |  |  | 2012-05-11 | 0 | #N/A
2012-05-18 | 0% | #N/A |  |  | 2012-05-18 | 0 | #N/A |  |  | 2012-05-18 | 0 | #N/A |  |  | 2012-05-18 | 0 | #N/A
2012-05-25 | 0% | #N/A |  |  | 2012-05-25 | 0 | #N/A |  |  | 2012-05-25 | 0 | #N/A |  |  | 2012-05-25 | 0 | #N/A
2012-06-01 | 0% | #N/A |  |  | 2012-06-01 | 0 | #N/A |  |  | 2012-06-01 | 0 | #N/A |  |  | 2012-06-01 | 0 | #N/A
2012-06-08 | 0% | #N/A |  |  | 2012-06-08 | 0 | #N/A |  |  | 2012-06-08 | 0 | #N/A |  |  | 2012-06-08 | 0 | #N/A |  |  |  | insert a picture here of the site progress
2012-06-15 | 0% | #N/A |  |  | 2012-06-15 | 0 | #N/A |  |  | 2012-06-15 | 0 | #N/A |  |  | 2012-06-15 | 0 | #N/A
2012-06-22 | 0% | #N/A |  |  | 2012-06-22 | 0 | #N/A |  |  | 2012-06-22 | 0 | #N/A |  |  | 2012-06-22 | 0 | #N/A
2012-06-29 | 0% | #N/A |  |  | 2012-06-29 | 0 | #N/A |  |  | 2012-06-29 | 0 | #N/A |  |  | 2012-06-29 | 0 | #N/A
2012-07-06 | 0% | #N/A |  |  | 2012-07-06 | 0 | #N/A |  |  | 2012-07-06 | 0 | #N/A |  |  | 2012-07-06 | 0 | #N/A
2012-07-13 | 0% | #N/A |  |  | 2012-07-13 | 0 | #N/A |  |  | 2012-07-13 | 0 | #N/A |  |  | 2012-07-13 | 0 | #N/A
2012-07-20 | 0% | #N/A |  |  | 2012-07-20 | 0 | #N/A |  |  | 2012-07-20 | 0 | #N/A |  |  | 2012-07-20 | 0 | #N/A
2012-07-27 | 0% | #N/A |  |  | 2012-07-27 | 0 | #N/A |  |  | 2012-07-27 | 0 | #N/A |  |  | 2012-07-27 | 0 | #N/A
2012-08-03 | 0% | #N/A |  |  | 2012-08-03 | 0 | #N/A |  |  | 2012-08-03 | 0 | #N/A |  |  | 2012-08-03 | 0 | #N/A |  |  | Top soil removal |  |  | Foundation Civil Works |  |  | GENERAL EXCAVATIONS
2012-08-10 | 0% | #N/A |  |  | 2012-08-10 | 0 | #N/A |  |  | 2012-08-10 | 0 | #N/A |  |  | 2012-08-10 | 0 | #N/A
2012-08-17 | 0% | #N/A |  |  | 2012-08-17 | 0 | #N/A |  |  | 2012-08-17 | 0 | #N/A |  |  | 2012-08-17 | 0 | #N/A
2012-08-24 | 0% | #N/A |  |  | 2012-08-24 | 0 | #N/A |  |  | 2012-08-24 | 0 | #N/A |  |  | 2012-08-24 | 0 | #N/A
2012-08-31 | 0% | #N/A |  |  | 2012-08-31 | 0 | #N/A |  |  | 2012-08-31 | 0 | #N/A |  |  | 2012-08-31 | 0 | #N/A
2012-09-07 | 0% | #N/A |  |  | 2012-09-07 | 0 | #N/A |  |  | 2012-09-07 | 0 | #N/A |  |  | 2012-09-07 | 0 | #N/A
2012-09-14 | 0% | #N/A |  |  | 2012-09-14 | 0 | #N/A |  |  | 2012-09-14 | 0 | #N/A |  |  | 2012-09-14 | 0 | #N/A
2012-09-21 | 0% | #N/A |  |  | 2012-09-21 | 0 | #N/A |  |  | 2012-09-21 | 0 | #N/A |  |  | 2012-09-21 | 0 | #N/A
2012-09-28 | 0% | #N/A |  |  | 2012-09-28 | 0 | #N/A |  |  | 2012-09-28 | 0 | #N/A |  |  | 2012-09-28 | 0 | #N/A
2012-10-05 | 0% | #N/A |  |  | 2012-10-05 | 0 | #N/A |  |  | 2012-10-05 | 0 | #N/A |  |  | 2012-10-05 | 0 | #N/A
2012-10-12 | 0% | #N/A |  |  | 2012-10-12 | 0 | #N/A |  |  | 2012-10-12 | 0 | #N/A |  |  | 2012-10-12 | 0 | #N/A
2012-10-19 | 0% | #N/A |  |  | 2012-10-19 | 0 | #N/A |  |  | 2012-10-19 | 0 | #N/A |  |  | 2012-10-19 | 0 | #N/A
2012-10-26 | 0% | #N/A |  |  | 2012-10-26 | 0 | #N/A |  |  | 2012-10-26 | 0 | #N/A |  |  | 2012-10-26 | 0 | #N/A
2012-11-02 | 0% | #N/A |  |  | 2012-11-02 | 0 | #N/A |  |  | 2012-11-02 | 0 | #N/A |  |  | 2012-11-02 | 0 | #N/A
2012-11-09 | 0% | #N/A |  |  | 2012-11-09 | 0 | #N/A |  |  | 2012-11-09 | 0 | #N/A |  |  | 2012-11-09 | 0 | #N/A
2012-11-16 | 0% | #N/A |  |  | 2012-11-16 | 0 | #N/A |  |  | 2012-11-16 | 0 | #N/A |  |  | 2012-11-16 | 0 | #N/A
2012-11-23 | 0% | #N/A |  |  | 2012-11-23 | 0 | #N/A |  |  | 2012-11-23 | 0 | #N/A |  |  | 2012-11-23 | 0 | #N/A
2012-11-30 | 0% | #N/A |  |  | 2012-11-30 | 0 | #N/A |  |  | 2012-11-30 | 0 | #N/A |  |  | 2012-11-30 | 0 | #N/A
2012-12-07 | 0% | #N/A |  |  | 2012-12-07 | 0 | #N/A |  |  | 2012-12-07 | 0 | #N/A |  |  | 2012-12-07 | 0 | #N/A
2012-12-14 | 0% | #N/A |  |  | 2012-12-14 | 0 | #N/A |  |  | 2012-12-14 | 0 | #N/A |  |  | 2012-12-14 | 0 | #N/A
2012-12-21 | 0% | #N/A |  |  | 2012-12-21 | 0 | #N/A |  |  | 2012-12-21 | 0 | #N/A |  |  | 2012-12-21 | 0 | #N/A
2012-12-28 | 0% | #N/A |  |  | 2012-12-28 | 0 | #N/A |  |  | 2012-12-28 | 0 | #N/A |  |  | 2012-12-28 | 0 | #N/A
2013-01-04 | 0% | #N/A |  |  | 2013-01-04 | 0 | #N/A |  |  | 2013-01-04 | 0 | #N/A |  |  | 2013-01-04 | 0 | #N/A
2013-01-11 | 0% | #N/A |  |  | 2013-01-11 | 0 | #N/A |  |  | 2013-01-11 | 0 | #N/A |  |  | 2013-01-11 | 0 | #N/A
2013-01-18 | 0% | #N/A |  |  | 2013-01-18 | 0 | #N/A |  |  | 2013-01-18 | 0 | #N/A |  |  | 2013-01-18 | 0 | #N/A
2013-01-25 | 0% | #N/A |  |  | 2013-01-25 | 0 | #N/A |  |  | 2013-01-25 | 0 | #N/A |  |  | 2013-01-25 | 0 | #N/A
2013-02-01 | 0% | #N/A |  |  | 2013-02-01 | 0 | #N/A |  |  | 2013-02-01 | 0 | #N/A |  |  | 2013-02-01 | 0 | #N/A
2013-02-08 | 0% | #N/A |  |  | 2013-02-08 | 0 | #N/A |  |  | 2013-02-08 | 0 | #N/A |  |  | 2013-02-08 | 0 | #N/A
2013-02-15 | 0% | #N/A |  |  | 2013-02-15 | 0 | #N/A |  |  | 2013-02-15 | 0 | #N/A |  |  | 2013-02-15 | 0 | #N/A
2013-02-22 | 0% | #N/A |  |  | 2013-02-22 | 0 | #N/A |  |  | 2013-02-22 | 0 | #N/A |  |  | 2013-02-22 | 0 | #N/A

## WBS
WBS Code | WBS Name | Level | WBS Number | 60
Baseline | Project | 1 | Max Level | 6
Baseline.01 | MILESTONES | 2
Baseline.02 | MANAGEMENT | 2
Baseline.03 | GENERAL | 2
Baseline.04 | ENGINEERING | 2
Baseline.04.01 | CIVIL | 3
Baseline.04.02 | STRUCTURAL | 3
Baseline.04.03 | MECHANICAL | 3
Baseline.04.04 | PIPING | 3
Baseline.04.05 | ELECTRICAL | 3
Baseline.04.06 | INSTRUMENTATION | 3
Baseline.05 | PROCUREMENT | 2
Baseline.05.01 | LONG LEAD | 3
Baseline.05.02 | ITEMIZED EQUIPEMENT | 3
Baseline.05.03 | BULK MATERIAL | 3
Baseline.06 | CONSTRUCTION | 2
Baseline.06.01 | GENERAL | 3
Baseline.06.01.01 | GENERAL AREA | 4
Baseline.06.01.01.01 | CIVIL | 5
Baseline.06.01.01.02 | STRUCTURAL | 5
Baseline.06.01.01.03 | MECHANICAL | 5
Baseline.06.01.01.04 | PIPING | 5
Baseline.06.01.01.05 | ELECTRICAL | 5
Baseline.06.01.01.06 | INSTRUMENTATION | 5
Baseline.06.02 | PROCESS | 3
Baseline.06.02.01 | MAIN PUMPS AREA | 4
Baseline.06.02.01.01 | PUMP 01-PR-02 | 5
Baseline.06.02.01.01.01 | CIVIL | 6
Baseline.06.02.01.01.02 | STRUCTURAL | 6
Baseline.06.02.01.01.03 | MECHANICAL | 6
Baseline.06.02.01.01.04 | PIPING | 6
Baseline.06.02.01.01.05 | ELECTRICAL | 6
Baseline.06.02.01.01.06 | INSTRUMENTATION | 6
Baseline.06.02.01.02 | PUMP 01-PR-03 | 5
Baseline.06.02.01.02.01 | CIVIL | 6
Baseline.06.02.01.02.02 | STRUCTURAL | 6
Baseline.06.02.01.02.03 | MECHANICAL | 6
Baseline.06.02.01.02.04 | PIPING | 6
Baseline.06.02.01.02.05 | ELECTRICAL | 6
Baseline.06.02.01.02.06 | INSTRUMENTATION | 6
Baseline.06.02.01.03 | PUMP 01-PR-04 | 5
Baseline.06.02.01.03.01 | CIVIL | 6
Baseline.06.02.01.03.02 | STRUCTURAL | 6
Baseline.06.02.01.03.03 | MECHANICAL | 6
Baseline.06.02.01.03.04 | PIPING | 6
Baseline.06.02.01.03.05 | ELECTRICAL | 6
Baseline.06.02.01.03.06 | INSTRUMENTATION | 6
Baseline.06.02.01.04 | PUMP 01-PR-05 | 5
Baseline.06.02.01.04.01 | CIVIL | 6
Baseline.06.02.01.04.02 | STRUCTURAL | 6
Baseline.06.02.01.04.03 | MECHANICAL | 6
Baseline.06.02.01.04.04 | PIPING | 6
Baseline.06.02.01.04.05 | ELECTRICAL | 6
Baseline.06.02.01.04.06 | INSTRUMENTATION | 6
Baseline.06.02.02 | PIPERACK AREA | 4
Baseline.06.03 | UTILITIES | 3
Baseline.06.04 | TANK FARM | 3
Baseline.07 | PRECOMMISSIONING | 2
Baseline.08 | COMMISSIONING | 2
Baseline.09 | START UP | 2

## WBS_Split
key | WBS Code | Level | Find "." | Find the previous "." | Level_Description | WBS Code | Level | Max_Roww | Max_Level
1Baseline | Baseline | 1 | 9 | 0 | Baseline | Project | 1 | 361 | 6
1Baseline.01 | Baseline.01 | 1 | 9 | 0 | Baseline | Project | 2
1Baseline.02 | Baseline.02 | 1 | 9 | 0 | Baseline | Project | 3
1Baseline.03 | Baseline.03 | 1 | 9 | 0 | Baseline | Project | 4
1Baseline.04 | Baseline.04 | 1 | 9 | 0 | Baseline | Project | 5
1Baseline.04.01 | Baseline.04.01 | 1 | 9 | 0 | Baseline | Project | 6
1Baseline.04.02 | Baseline.04.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.04.03 | Baseline.04.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.04.04 | Baseline.04.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.04.05 | Baseline.04.05 | 1 | 9 | 0 | Baseline | Project
1Baseline.04.06 | Baseline.04.06 | 1 | 9 | 0 | Baseline | Project
1Baseline.05 | Baseline.05 | 1 | 9 | 0 | Baseline | Project
1Baseline.05.01 | Baseline.05.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.05.02 | Baseline.05.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.05.03 | Baseline.05.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06 | Baseline.06 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01 | Baseline.06.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01.01 | Baseline.06.01.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01.01.01 | Baseline.06.01.01.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01.01.02 | Baseline.06.01.01.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01.01.03 | Baseline.06.01.01.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01.01.04 | Baseline.06.01.01.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01.01.05 | Baseline.06.01.01.05 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.01.01.06 | Baseline.06.01.01.06 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02 | Baseline.06.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01 | Baseline.06.02.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.01 | Baseline.06.02.01.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.01.01 | Baseline.06.02.01.01.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.01.02 | Baseline.06.02.01.01.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.01.03 | Baseline.06.02.01.01.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.01.04 | Baseline.06.02.01.01.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.01.05 | Baseline.06.02.01.01.05 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.01.06 | Baseline.06.02.01.01.06 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.02 | Baseline.06.02.01.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.02.01 | Baseline.06.02.01.02.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.02.02 | Baseline.06.02.01.02.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.02.03 | Baseline.06.02.01.02.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.02.04 | Baseline.06.02.01.02.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.02.05 | Baseline.06.02.01.02.05 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.02.06 | Baseline.06.02.01.02.06 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.03 | Baseline.06.02.01.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.03.01 | Baseline.06.02.01.03.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.03.02 | Baseline.06.02.01.03.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.03.03 | Baseline.06.02.01.03.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.03.04 | Baseline.06.02.01.03.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.03.05 | Baseline.06.02.01.03.05 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.03.06 | Baseline.06.02.01.03.06 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.04 | Baseline.06.02.01.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.04.01 | Baseline.06.02.01.04.01 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.04.02 | Baseline.06.02.01.04.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.04.03 | Baseline.06.02.01.04.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.04.04 | Baseline.06.02.01.04.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.04.05 | Baseline.06.02.01.04.05 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.01.04.06 | Baseline.06.02.01.04.06 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.02.02 | Baseline.06.02.02 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.03 | Baseline.06.03 | 1 | 9 | 0 | Baseline | Project
1Baseline.06.04 | Baseline.06.04 | 1 | 9 | 0 | Baseline | Project
1Baseline.07 | Baseline.07 | 1 | 9 | 0 | Baseline | Project
1Baseline.08 | Baseline.08 | 1 | 9 | 0 | Baseline | Project
1Baseline.09 | Baseline.09 | 1 | 9 | 0 | Baseline | Project
2Baseline | Baseline | 2 | 9 | 9
2Baseline.01 | Baseline.01 | 2 | 12 | 9 | Baseline.01 | MILESTONES
2Baseline.02 | Baseline.02 | 2 | 12 | 9 | Baseline.02 | MANAGEMENT
2Baseline.03 | Baseline.03 | 2 | 12 | 9 | Baseline.03 | GENERAL
2Baseline.04 | Baseline.04 | 2 | 12 | 9 | Baseline.04 | ENGINEERING
2Baseline.04.01 | Baseline.04.01 | 2 | 12 | 9 | Baseline.04 | ENGINEERING
2Baseline.04.02 | Baseline.04.02 | 2 | 12 | 9 | Baseline.04 | ENGINEERING
2Baseline.04.03 | Baseline.04.03 | 2 | 12 | 9 | Baseline.04 | ENGINEERING
2Baseline.04.04 | Baseline.04.04 | 2 | 12 | 9 | Baseline.04 | ENGINEERING
2Baseline.04.05 | Baseline.04.05 | 2 | 12 | 9 | Baseline.04 | ENGINEERING
2Baseline.04.06 | Baseline.04.06 | 2 | 12 | 9 | Baseline.04 | ENGINEERING
2Baseline.05 | Baseline.05 | 2 | 12 | 9 | Baseline.05 | PROCUREMENT
2Baseline.05.01 | Baseline.05.01 | 2 | 12 | 9 | Baseline.05 | PROCUREMENT
2Baseline.05.02 | Baseline.05.02 | 2 | 12 | 9 | Baseline.05 | PROCUREMENT
2Baseline.05.03 | Baseline.05.03 | 2 | 12 | 9 | Baseline.05 | PROCUREMENT
2Baseline.06 | Baseline.06 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01 | Baseline.06.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01.01 | Baseline.06.01.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01.01.01 | Baseline.06.01.01.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01.01.02 | Baseline.06.01.01.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01.01.03 | Baseline.06.01.01.03 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01.01.04 | Baseline.06.01.01.04 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01.01.05 | Baseline.06.01.01.05 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.01.01.06 | Baseline.06.01.01.06 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02 | Baseline.06.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01 | Baseline.06.02.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.01 | Baseline.06.02.01.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.01.01 | Baseline.06.02.01.01.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.01.02 | Baseline.06.02.01.01.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.01.03 | Baseline.06.02.01.01.03 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.01.04 | Baseline.06.02.01.01.04 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.01.05 | Baseline.06.02.01.01.05 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.01.06 | Baseline.06.02.01.01.06 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.02 | Baseline.06.02.01.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.02.01 | Baseline.06.02.01.02.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.02.02 | Baseline.06.02.01.02.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.02.03 | Baseline.06.02.01.02.03 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.02.04 | Baseline.06.02.01.02.04 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.02.05 | Baseline.06.02.01.02.05 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.02.06 | Baseline.06.02.01.02.06 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.03 | Baseline.06.02.01.03 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.03.01 | Baseline.06.02.01.03.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.03.02 | Baseline.06.02.01.03.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.03.03 | Baseline.06.02.01.03.03 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.03.04 | Baseline.06.02.01.03.04 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.03.05 | Baseline.06.02.01.03.05 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.03.06 | Baseline.06.02.01.03.06 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.04 | Baseline.06.02.01.04 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.04.01 | Baseline.06.02.01.04.01 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.04.02 | Baseline.06.02.01.04.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.04.03 | Baseline.06.02.01.04.03 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.04.04 | Baseline.06.02.01.04.04 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.04.05 | Baseline.06.02.01.04.05 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.01.04.06 | Baseline.06.02.01.04.06 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.02.02 | Baseline.06.02.02 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.03 | Baseline.06.03 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.06.04 | Baseline.06.04 | 2 | 12 | 9 | Baseline.06 | CONSTRUCTION
2Baseline.07 | Baseline.07 | 2 | 12 | 9 | Baseline.07 | PRECOMMISSIONING
2Baseline.08 | Baseline.08 | 2 | 12 | 9 | Baseline.08 | COMMISSIONING
2Baseline.09 | Baseline.09 | 2 | 12 | 9 | Baseline.09 | START UP
3Baseline | Baseline | 3 | 9 | 9
3Baseline.01 | Baseline.01 | 3 | 12 | 12
3Baseline.02 | Baseline.02 | 3 | 12 | 12
3Baseline.03 | Baseline.03 | 3 | 12 | 12
3Baseline.04 | Baseline.04 | 3 | 12 | 12
3Baseline.04.01 | Baseline.04.01 | 3 | 15 | 12 | Baseline.04.01 | CIVIL
3Baseline.04.02 | Baseline.04.02 | 3 | 15 | 12 | Baseline.04.02 | STRUCTURAL
3Baseline.04.03 | Baseline.04.03 | 3 | 15 | 12 | Baseline.04.03 | MECHANICAL
3Baseline.04.04 | Baseline.04.04 | 3 | 15 | 12 | Baseline.04.04 | PIPING
3Baseline.04.05 | Baseline.04.05 | 3 | 15 | 12 | Baseline.04.05 | ELECTRICAL
3Baseline.04.06 | Baseline.04.06 | 3 | 15 | 12 | Baseline.04.06 | INSTRUMENTATION
3Baseline.05 | Baseline.05 | 3 | 12 | 12
3Baseline.05.01 | Baseline.05.01 | 3 | 15 | 12 | Baseline.05.01 | LONG LEAD
3Baseline.05.02 | Baseline.05.02 | 3 | 15 | 12 | Baseline.05.02 | ITEMIZED EQUIPEMENT
3Baseline.05.03 | Baseline.05.03 | 3 | 15 | 12 | Baseline.05.03 | BULK MATERIAL
3Baseline.06 | Baseline.06 | 3 | 12 | 12
3Baseline.06.01 | Baseline.06.01 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.01.01 | Baseline.06.01.01 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.01.01.01 | Baseline.06.01.01.01 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.01.01.02 | Baseline.06.01.01.02 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.01.01.03 | Baseline.06.01.01.03 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.01.01.04 | Baseline.06.01.01.04 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.01.01.05 | Baseline.06.01.01.05 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.01.01.06 | Baseline.06.01.01.06 | 3 | 15 | 12 | Baseline.06.01 | GENERAL
3Baseline.06.02 | Baseline.06.02 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01 | Baseline.06.02.01 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.01 | Baseline.06.02.01.01 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.01.01 | Baseline.06.02.01.01.01 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.01.02 | Baseline.06.02.01.01.02 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.01.03 | Baseline.06.02.01.01.03 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.01.04 | Baseline.06.02.01.01.04 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.01.05 | Baseline.06.02.01.01.05 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.01.06 | Baseline.06.02.01.01.06 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.02 | Baseline.06.02.01.02 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.02.01 | Baseline.06.02.01.02.01 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.02.02 | Baseline.06.02.01.02.02 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.02.03 | Baseline.06.02.01.02.03 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.02.04 | Baseline.06.02.01.02.04 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.02.05 | Baseline.06.02.01.02.05 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.02.06 | Baseline.06.02.01.02.06 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.03 | Baseline.06.02.01.03 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.03.01 | Baseline.06.02.01.03.01 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.03.02 | Baseline.06.02.01.03.02 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.03.03 | Baseline.06.02.01.03.03 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.03.04 | Baseline.06.02.01.03.04 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.03.05 | Baseline.06.02.01.03.05 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.03.06 | Baseline.06.02.01.03.06 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.04 | Baseline.06.02.01.04 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.04.01 | Baseline.06.02.01.04.01 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.04.02 | Baseline.06.02.01.04.02 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.04.03 | Baseline.06.02.01.04.03 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.04.04 | Baseline.06.02.01.04.04 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.04.05 | Baseline.06.02.01.04.05 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.01.04.06 | Baseline.06.02.01.04.06 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.02.02 | Baseline.06.02.02 | 3 | 15 | 12 | Baseline.06.02 | PROCESS
3Baseline.06.03 | Baseline.06.03 | 3 | 15 | 12 | Baseline.06.03 | UTILITIES
3Baseline.06.04 | Baseline.06.04 | 3 | 15 | 12 | Baseline.06.04 | TANK FARM
3Baseline.07 | Baseline.07 | 3 | 12 | 12
3Baseline.08 | Baseline.08 | 3 | 12 | 12
3Baseline.09 | Baseline.09 | 3 | 12 | 12
4Baseline | Baseline | 4 | 9 | 9
4Baseline.01 | Baseline.01 | 4 | 12 | 12
4Baseline.02 | Baseline.02 | 4 | 12 | 12
4Baseline.03 | Baseline.03 | 4 | 12 | 12
4Baseline.04 | Baseline.04 | 4 | 12 | 12
4Baseline.04.01 | Baseline.04.01 | 4 | 15 | 15
4Baseline.04.02 | Baseline.04.02 | 4 | 15 | 15
4Baseline.04.03 | Baseline.04.03 | 4 | 15 | 15
4Baseline.04.04 | Baseline.04.04 | 4 | 15 | 15
4Baseline.04.05 | Baseline.04.05 | 4 | 15 | 15
4Baseline.04.06 | Baseline.04.06 | 4 | 15 | 15
4Baseline.05 | Baseline.05 | 4 | 12 | 12
4Baseline.05.01 | Baseline.05.01 | 4 | 15 | 15
4Baseline.05.02 | Baseline.05.02 | 4 | 15 | 15
4Baseline.05.03 | Baseline.05.03 | 4 | 15 | 15
4Baseline.06 | Baseline.06 | 4 | 12 | 12
4Baseline.06.01 | Baseline.06.01 | 4 | 15 | 15
4Baseline.06.01.01 | Baseline.06.01.01 | 4 | 18 | 15 | Baseline.06.01.01 | GENERAL AREA
4Baseline.06.01.01.01 | Baseline.06.01.01.01 | 4 | 18 | 15 | Baseline.06.01.01 | GENERAL AREA
4Baseline.06.01.01.02 | Baseline.06.01.01.02 | 4 | 18 | 15 | Baseline.06.01.01 | GENERAL AREA
4Baseline.06.01.01.03 | Baseline.06.01.01.03 | 4 | 18 | 15 | Baseline.06.01.01 | GENERAL AREA
4Baseline.06.01.01.04 | Baseline.06.01.01.04 | 4 | 18 | 15 | Baseline.06.01.01 | GENERAL AREA
4Baseline.06.01.01.05 | Baseline.06.01.01.05 | 4 | 18 | 15 | Baseline.06.01.01 | GENERAL AREA
4Baseline.06.01.01.06 | Baseline.06.01.01.06 | 4 | 18 | 15 | Baseline.06.01.01 | GENERAL AREA
4Baseline.06.02 | Baseline.06.02 | 4 | 15 | 15
4Baseline.06.02.01 | Baseline.06.02.01 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.01 | Baseline.06.02.01.01 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.01.01 | Baseline.06.02.01.01.01 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.01.02 | Baseline.06.02.01.01.02 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.01.03 | Baseline.06.02.01.01.03 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.01.04 | Baseline.06.02.01.01.04 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.01.05 | Baseline.06.02.01.01.05 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.01.06 | Baseline.06.02.01.01.06 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.02 | Baseline.06.02.01.02 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.02.01 | Baseline.06.02.01.02.01 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.02.02 | Baseline.06.02.01.02.02 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.02.03 | Baseline.06.02.01.02.03 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.02.04 | Baseline.06.02.01.02.04 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.02.05 | Baseline.06.02.01.02.05 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.02.06 | Baseline.06.02.01.02.06 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.03 | Baseline.06.02.01.03 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.03.01 | Baseline.06.02.01.03.01 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.03.02 | Baseline.06.02.01.03.02 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.03.03 | Baseline.06.02.01.03.03 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.03.04 | Baseline.06.02.01.03.04 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.03.05 | Baseline.06.02.01.03.05 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.03.06 | Baseline.06.02.01.03.06 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.04 | Baseline.06.02.01.04 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.04.01 | Baseline.06.02.01.04.01 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.04.02 | Baseline.06.02.01.04.02 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.04.03 | Baseline.06.02.01.04.03 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.04.04 | Baseline.06.02.01.04.04 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.04.05 | Baseline.06.02.01.04.05 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.01.04.06 | Baseline.06.02.01.04.06 | 4 | 18 | 15 | Baseline.06.02.01 | MAIN PUMPS AREA
4Baseline.06.02.02 | Baseline.06.02.02 | 4 | 18 | 15 | Baseline.06.02.02 | PIPERACK AREA
4Baseline.06.03 | Baseline.06.03 | 4 | 15 | 15
4Baseline.06.04 | Baseline.06.04 | 4 | 15 | 15
4Baseline.07 | Baseline.07 | 4 | 12 | 12
4Baseline.08 | Baseline.08 | 4 | 12 | 12
4Baseline.09 | Baseline.09 | 4 | 12 | 12
5Baseline | Baseline | 5 | 9 | 9
5Baseline.01 | Baseline.01 | 5 | 12 | 12
5Baseline.02 | Baseline.02 | 5 | 12 | 12
5Baseline.03 | Baseline.03 | 5 | 12 | 12
5Baseline.04 | Baseline.04 | 5 | 12 | 12
5Baseline.04.01 | Baseline.04.01 | 5 | 15 | 15
5Baseline.04.02 | Baseline.04.02 | 5 | 15 | 15
5Baseline.04.03 | Baseline.04.03 | 5 | 15 | 15
5Baseline.04.04 | Baseline.04.04 | 5 | 15 | 15
5Baseline.04.05 | Baseline.04.05 | 5 | 15 | 15
5Baseline.04.06 | Baseline.04.06 | 5 | 15 | 15
5Baseline.05 | Baseline.05 | 5 | 12 | 12
5Baseline.05.01 | Baseline.05.01 | 5 | 15 | 15
5Baseline.05.02 | Baseline.05.02 | 5 | 15 | 15
5Baseline.05.03 | Baseline.05.03 | 5 | 15 | 15
5Baseline.06 | Baseline.06 | 5 | 12 | 12
5Baseline.06.01 | Baseline.06.01 | 5 | 15 | 15
5Baseline.06.01.01 | Baseline.06.01.01 | 5 | 18 | 18
5Baseline.06.01.01.01 | Baseline.06.01.01.01 | 5 | 21 | 18 | Baseline.06.01.01.01 | CIVIL
5Baseline.06.01.01.02 | Baseline.06.01.01.02 | 5 | 21 | 18 | Baseline.06.01.01.02 | STRUCTURAL
5Baseline.06.01.01.03 | Baseline.06.01.01.03 | 5 | 21 | 18 | Baseline.06.01.01.03 | MECHANICAL
5Baseline.06.01.01.04 | Baseline.06.01.01.04 | 5 | 21 | 18 | Baseline.06.01.01.04 | PIPING
5Baseline.06.01.01.05 | Baseline.06.01.01.05 | 5 | 21 | 18 | Baseline.06.01.01.05 | ELECTRICAL
5Baseline.06.01.01.06 | Baseline.06.01.01.06 | 5 | 21 | 18 | Baseline.06.01.01.06 | INSTRUMENTATION
5Baseline.06.02 | Baseline.06.02 | 5 | 15 | 15
5Baseline.06.02.01 | Baseline.06.02.01 | 5 | 18 | 18
5Baseline.06.02.01.01 | Baseline.06.02.01.01 | 5 | 21 | 18 | Baseline.06.02.01.01 | PUMP 01-PR-02
5Baseline.06.02.01.01.01 | Baseline.06.02.01.01.01 | 5 | 21 | 18 | Baseline.06.02.01.01 | PUMP 01-PR-02
5Baseline.06.02.01.01.02 | Baseline.06.02.01.01.02 | 5 | 21 | 18 | Baseline.06.02.01.01 | PUMP 01-PR-02
5Baseline.06.02.01.01.03 | Baseline.06.02.01.01.03 | 5 | 21 | 18 | Baseline.06.02.01.01 | PUMP 01-PR-02
5Baseline.06.02.01.01.04 | Baseline.06.02.01.01.04 | 5 | 21 | 18 | Baseline.06.02.01.01 | PUMP 01-PR-02
5Baseline.06.02.01.01.05 | Baseline.06.02.01.01.05 | 5 | 21 | 18 | Baseline.06.02.01.01 | PUMP 01-PR-02
5Baseline.06.02.01.01.06 | Baseline.06.02.01.01.06 | 5 | 21 | 18 | Baseline.06.02.01.01 | PUMP 01-PR-02
5Baseline.06.02.01.02 | Baseline.06.02.01.02 | 5 | 21 | 18 | Baseline.06.02.01.02 | PUMP 01-PR-03
5Baseline.06.02.01.02.01 | Baseline.06.02.01.02.01 | 5 | 21 | 18 | Baseline.06.02.01.02 | PUMP 01-PR-03
5Baseline.06.02.01.02.02 | Baseline.06.02.01.02.02 | 5 | 21 | 18 | Baseline.06.02.01.02 | PUMP 01-PR-03
5Baseline.06.02.01.02.03 | Baseline.06.02.01.02.03 | 5 | 21 | 18 | Baseline.06.02.01.02 | PUMP 01-PR-03
5Baseline.06.02.01.02.04 | Baseline.06.02.01.02.04 | 5 | 21 | 18 | Baseline.06.02.01.02 | PUMP 01-PR-03
5Baseline.06.02.01.02.05 | Baseline.06.02.01.02.05 | 5 | 21 | 18 | Baseline.06.02.01.02 | PUMP 01-PR-03
5Baseline.06.02.01.02.06 | Baseline.06.02.01.02.06 | 5 | 21 | 18 | Baseline.06.02.01.02 | PUMP 01-PR-03
5Baseline.06.02.01.03 | Baseline.06.02.01.03 | 5 | 21 | 18 | Baseline.06.02.01.03 | PUMP 01-PR-04
5Baseline.06.02.01.03.01 | Baseline.06.02.01.03.01 | 5 | 21 | 18 | Baseline.06.02.01.03 | PUMP 01-PR-04
5Baseline.06.02.01.03.02 | Baseline.06.02.01.03.02 | 5 | 21 | 18 | Baseline.06.02.01.03 | PUMP 01-PR-04
5Baseline.06.02.01.03.03 | Baseline.06.02.01.03.03 | 5 | 21 | 18 | Baseline.06.02.01.03 | PUMP 01-PR-04
5Baseline.06.02.01.03.04 | Baseline.06.02.01.03.04 | 5 | 21 | 18 | Baseline.06.02.01.03 | PUMP 01-PR-04
5Baseline.06.02.01.03.05 | Baseline.06.02.01.03.05 | 5 | 21 | 18 | Baseline.06.02.01.03 | PUMP 01-PR-04
5Baseline.06.02.01.03.06 | Baseline.06.02.01.03.06 | 5 | 21 | 18 | Baseline.06.02.01.03 | PUMP 01-PR-04
5Baseline.06.02.01.04 | Baseline.06.02.01.04 | 5 | 21 | 18 | Baseline.06.02.01.04 | PUMP 01-PR-05
5Baseline.06.02.01.04.01 | Baseline.06.02.01.04.01 | 5 | 21 | 18 | Baseline.06.02.01.04 | PUMP 01-PR-05
5Baseline.06.02.01.04.02 | Baseline.06.02.01.04.02 | 5 | 21 | 18 | Baseline.06.02.01.04 | PUMP 01-PR-05
5Baseline.06.02.01.04.03 | Baseline.06.02.01.04.03 | 5 | 21 | 18 | Baseline.06.02.01.04 | PUMP 01-PR-05
5Baseline.06.02.01.04.04 | Baseline.06.02.01.04.04 | 5 | 21 | 18 | Baseline.06.02.01.04 | PUMP 01-PR-05
5Baseline.06.02.01.04.05 | Baseline.06.02.01.04.05 | 5 | 21 | 18 | Baseline.06.02.01.04 | PUMP 01-PR-05
5Baseline.06.02.01.04.06 | Baseline.06.02.01.04.06 | 5 | 21 | 18 | Baseline.06.02.01.04 | PUMP 01-PR-05
5Baseline.06.02.02 | Baseline.06.02.02 | 5 | 18 | 18
5Baseline.06.03 | Baseline.06.03 | 5 | 15 | 15
5Baseline.06.04 | Baseline.06.04 | 5 | 15 | 15
5Baseline.07 | Baseline.07 | 5 | 12 | 12
5Baseline.08 | Baseline.08 | 5 | 12 | 12
5Baseline.09 | Baseline.09 | 5 | 12 | 12
6Baseline | Baseline | 6 | 9 | 9
6Baseline.01 | Baseline.01 | 6 | 12 | 12
6Baseline.02 | Baseline.02 | 6 | 12 | 12
6Baseline.03 | Baseline.03 | 6 | 12 | 12
6Baseline.04 | Baseline.04 | 6 | 12 | 12
6Baseline.04.01 | Baseline.04.01 | 6 | 15 | 15
6Baseline.04.02 | Baseline.04.02 | 6 | 15 | 15
6Baseline.04.03 | Baseline.04.03 | 6 | 15 | 15
6Baseline.04.04 | Baseline.04.04 | 6 | 15 | 15
6Baseline.04.05 | Baseline.04.05 | 6 | 15 | 15
6Baseline.04.06 | Baseline.04.06 | 6 | 15 | 15
6Baseline.05 | Baseline.05 | 6 | 12 | 12
6Baseline.05.01 | Baseline.05.01 | 6 | 15 | 15
6Baseline.05.02 | Baseline.05.02 | 6 | 15 | 15
6Baseline.05.03 | Baseline.05.03 | 6 | 15 | 15
6Baseline.06 | Baseline.06 | 6 | 12 | 12
6Baseline.06.01 | Baseline.06.01 | 6 | 15 | 15
6Baseline.06.01.01 | Baseline.06.01.01 | 6 | 18 | 18
6Baseline.06.01.01.01 | Baseline.06.01.01.01 | 6 | 21 | 21
6Baseline.06.01.01.02 | Baseline.06.01.01.02 | 6 | 21 | 21
6Baseline.06.01.01.03 | Baseline.06.01.01.03 | 6 | 21 | 21
6Baseline.06.01.01.04 | Baseline.06.01.01.04 | 6 | 21 | 21
6Baseline.06.01.01.05 | Baseline.06.01.01.05 | 6 | 21 | 21
6Baseline.06.01.01.06 | Baseline.06.01.01.06 | 6 | 21 | 21
6Baseline.06.02 | Baseline.06.02 | 6 | 15 | 15
6Baseline.06.02.01 | Baseline.06.02.01 | 6 | 18 | 18
6Baseline.06.02.01.01 | Baseline.06.02.01.01 | 6 | 21 | 21
6Baseline.06.02.01.01.01 | Baseline.06.02.01.01.01 | 6 | 24 | 21 | Baseline.06.02.01.01.01 | CIVIL
6Baseline.06.02.01.01.02 | Baseline.06.02.01.01.02 | 6 | 24 | 21 | Baseline.06.02.01.01.02 | STRUCTURAL
6Baseline.06.02.01.01.03 | Baseline.06.02.01.01.03 | 6 | 24 | 21 | Baseline.06.02.01.01.03 | MECHANICAL
6Baseline.06.02.01.01.04 | Baseline.06.02.01.01.04 | 6 | 24 | 21 | Baseline.06.02.01.01.04 | PIPING
6Baseline.06.02.01.01.05 | Baseline.06.02.01.01.05 | 6 | 24 | 21 | Baseline.06.02.01.01.05 | ELECTRICAL
6Baseline.06.02.01.01.06 | Baseline.06.02.01.01.06 | 6 | 24 | 21 | Baseline.06.02.01.01.06 | INSTRUMENTATION
6Baseline.06.02.01.02 | Baseline.06.02.01.02 | 6 | 21 | 21
6Baseline.06.02.01.02.01 | Baseline.06.02.01.02.01 | 6 | 24 | 21 | Baseline.06.02.01.02.01 | CIVIL
6Baseline.06.02.01.02.02 | Baseline.06.02.01.02.02 | 6 | 24 | 21 | Baseline.06.02.01.02.02 | STRUCTURAL
6Baseline.06.02.01.02.03 | Baseline.06.02.01.02.03 | 6 | 24 | 21 | Baseline.06.02.01.02.03 | MECHANICAL
6Baseline.06.02.01.02.04 | Baseline.06.02.01.02.04 | 6 | 24 | 21 | Baseline.06.02.01.02.04 | PIPING
6Baseline.06.02.01.02.05 | Baseline.06.02.01.02.05 | 6 | 24 | 21 | Baseline.06.02.01.02.05 | ELECTRICAL
6Baseline.06.02.01.02.06 | Baseline.06.02.01.02.06 | 6 | 24 | 21 | Baseline.06.02.01.02.06 | INSTRUMENTATION
6Baseline.06.02.01.03 | Baseline.06.02.01.03 | 6 | 21 | 21
6Baseline.06.02.01.03.01 | Baseline.06.02.01.03.01 | 6 | 24 | 21 | Baseline.06.02.01.03.01 | CIVIL
6Baseline.06.02.01.03.02 | Baseline.06.02.01.03.02 | 6 | 24 | 21 | Baseline.06.02.01.03.02 | STRUCTURAL
6Baseline.06.02.01.03.03 | Baseline.06.02.01.03.03 | 6 | 24 | 21 | Baseline.06.02.01.03.03 | MECHANICAL
6Baseline.06.02.01.03.04 | Baseline.06.02.01.03.04 | 6 | 24 | 21 | Baseline.06.02.01.03.04 | PIPING
6Baseline.06.02.01.03.05 | Baseline.06.02.01.03.05 | 6 | 24 | 21 | Baseline.06.02.01.03.05 | ELECTRICAL
6Baseline.06.02.01.03.06 | Baseline.06.02.01.03.06 | 6 | 24 | 21 | Baseline.06.02.01.03.06 | INSTRUMENTATION
6Baseline.06.02.01.04 | Baseline.06.02.01.04 | 6 | 21 | 21
6Baseline.06.02.01.04.01 | Baseline.06.02.01.04.01 | 6 | 24 | 21 | Baseline.06.02.01.04.01 | CIVIL
6Baseline.06.02.01.04.02 | Baseline.06.02.01.04.02 | 6 | 24 | 21 | Baseline.06.02.01.04.02 | STRUCTURAL
6Baseline.06.02.01.04.03 | Baseline.06.02.01.04.03 | 6 | 24 | 21 | Baseline.06.02.01.04.03 | MECHANICAL
6Baseline.06.02.01.04.04 | Baseline.06.02.01.04.04 | 6 | 24 | 21 | Baseline.06.02.01.04.04 | PIPING
6Baseline.06.02.01.04.05 | Baseline.06.02.01.04.05 | 6 | 24 | 21 | Baseline.06.02.01.04.05 | ELECTRICAL
6Baseline.06.02.01.04.06 | Baseline.06.02.01.04.06 | 6 | 24 | 21 | Baseline.06.02.01.04.06 | INSTRUMENTATION
6Baseline.06.02.02 | Baseline.06.02.02 | 6 | 18 | 18
6Baseline.06.03 | Baseline.06.03 | 6 | 15 | 15
6Baseline.06.04 | Baseline.06.04 | 6 | 15 | 15
6Baseline.07 | Baseline.07 | 6 | 12 | 12
6Baseline.08 | Baseline.08 | 6 | 12 | 12
6Baseline.09 | Baseline.09 | 6 | 12 | 12

## Commodities
Commodity_ID | Commodity | UM
CW | Foundation Civil Works | M3
MC1 | EREC.OF ASSEMBLED MACHINERY | KG
FC | FIN.COAT FOR MACH./MEC.LIFTING | M2
TS | Top soil removal | M2
GE | GENERAL EXCAVATIONS | M3
GB | General backfil. of area/roads | M3

## Holidays
Holidays
2012-01-06
2012-01-19
2012-02-01
2012-02-14
2012-02-27
2012-03-11
2012-03-24
2012-04-06
2012-04-19
2012-05-02
2012-05-15
2012-05-28
2012-06-10
2012-06-23
2012-07-06
2012-07-19
2012-08-01
2012-08-14
2012-08-27
2012-09-09
2012-09-22
2012-10-05
2012-10-18
2012-10-31
2012-11-13
2012-11-26
2012-12-09
2012-12-22
2012-12-23
2012-12-24
2012-12-25
2012-12-26
2012-12-27
2012-12-28
2012-12-29
2012-12-30
2012-12-31
2013-01-01
2013-01-02
2013-01-03
2013-01-04
2013-01-06
2013-01-19
2013-02-01
2013-02-14
2013-01-07
2013-01-20
2013-02-02
2013-02-15
2013-01-08

## Period
Period_Id | Period | MaxRow
1 | 2012-01-06 | 1259
2 | 2012-01-13
3 | 2012-01-20
4 | 2012-01-27
5 | 2012-02-03
6 | 2012-02-10
7 | 2012-02-17
8 | 2012-02-24
9 | 2012-03-02
10 | 2012-03-09
11 | 2012-03-16
12 | 2012-03-23
13 | 2012-03-30
14 | 2012-04-06
15 | 2012-04-13
16 | 2012-04-20
17 | 2012-04-27
18 | 2012-05-04
19 | 2012-05-11
20 | 2012-05-18
21 | 2012-05-25
22 | 2012-06-01
23 | 2012-06-08
24 | 2012-06-15
25 | 2012-06-22
26 | 2012-06-29
27 | 2012-07-06
28 | 2012-07-13
29 | 2012-07-20
30 | 2012-07-27
31 | 2012-08-03
32 | 2012-08-10
33 | 2012-08-17
34 | 2012-08-24
35 | 2012-08-31
36 | 2012-09-07
37 | 2012-09-14
38 | 2012-09-21
39 | 2012-09-28
40 | 2012-10-05
41 | 2012-10-12
42 | 2012-10-19
43 | 2012-10-26
44 | 2012-11-02
45 | 2012-11-09
46 | 2012-11-16
47 | 2012-11-23
48 | 2012-11-30
49 | 2012-12-07
50 | 2012-12-14
51 | 2012-12-21
52 | 2012-12-28
53 | 2013-01-04
54 | 2013-01-11
55 | 2013-01-18
56 | 2013-01-25
57 | 2013-02-01
58 | 2013-02-08
59 | 2013-02-15
60 | 2013-02-22
Formulas:
Period = [Period, row above]+7

## Baseline
REV | ID | Planned_Quantity | Planned_budget | Planned_Start | Planned_Finish | OD | 2012-01-06 | 2012-01-13 | 2012-01-20 | 2012-01-27 | 2012-02-03 | 2012-02-10 | 2012-02-17 | 2012-02-24 | 2012-03-02 | 2012-03-09 | 2012-03-16 | 2012-03-23 | 2012-03-30 | 2012-04-06 | 2012-04-13 | 2012-04-20 | 2012-04-27 | 2012-05-04 | 2012-05-11 | 2012-05-18 | 2012-05-25 | 2012-06-01 | 2012-06-08 | 2012-06-15 | 2012-06-22 | 2012-06-29 | 2012-07-06 | 2012-07-13 | 2012-07-20 | 2012-07-27 | 2012-08-03 | 2012-08-10 | 2012-08-17 | 2012-08-24 | 2012-08-31 | 2012-09-07 | 2012-09-14 | 2012-09-21 | 2012-09-28 | 2012-10-05 | 2012-10-12 | 2012-10-19 | 2012-10-26 | 2012-11-02 | 2012-11-09 | 2012-11-16 | 2012-11-23 | 2012-11-30 | 2012-12-07 | 2012-12-14 | 2012-12-21 | 2012-12-28 | 2013-01-04 | 2013-01-11 | 2013-01-18 | 2013-01-25 | 2013-02-01 | 2013-02-08 | 2013-02-15 | 2013-02-22
0 | 1 | 253 | 1514.9701 | 2012-01-29 | 2012-02-26 | 27 | 0% | 0% | 0% | 0% | 18.52% | 44.44% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 2 | 15000 | 376.506 | 2012-01-29 | 2012-02-26 | 27 | 0% | 0% | 0% | 0% | 18.52% | 44.44% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 3 | 5000 | 6250 | 2012-02-26 | 2012-03-10 | 13 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 38.46% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 4 | 60 | 17.1429 | 2012-03-10 | 2012-03-15 | 5 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 5 | 2000 | 11976.0479 | 2012-03-15 | 2012-04-11 | 26 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.692% | 34.62% | 57.69% | 80.77% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 6 | 50000 | 1882.5301 | 2012-04-11 | 2012-04-25 | 14 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.43% | 64.29% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 7 | 50 | 62.5 | 2012-04-25 | 2012-05-23 | 27 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 33.33% | 59.26% | 81.48% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 8 | 60 | 17.1429 | 2012-05-23 | 2012-05-30 | 7 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 42.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 9 | 200 | 1197.6048 | 2012-05-30 | 2012-06-27 | 27 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 37.04% | 59.26% | 85.19% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 10 | 50000 | 1882.5301 | 2012-06-27 | 2012-07-11 | 14 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.43% | 64.29% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 11 | 500 | 625 | 2012-07-11 | 2012-08-08 | 27 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 33.33% | 59.26% | 81.48% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 12 | 400 | 114.2857 | 2012-08-08 | 2012-09-14 | 35 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.571% | 25.71% | 45.71% | 62.86% | 82.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 13 | 200 | 1197.6048 | 2012-09-14 | 2012-10-03 | 19 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.263% | 42.11% | 73.68% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 14 | 300 | 11.2952 | 2012-10-03 | 2012-10-17 | 14 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14.29% | 64.29% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 15 | 40 | 50 | 2012-10-17 | 2012-10-30 | 13 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15.38% | 69.23% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 16 | 50 | 14.2857 | 2012-10-30 | 2012-11-13 | 13 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.08% | 76.92% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 17 | 9000 | 300 | 2012-11-13 | 2012-12-12 | 27 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 37.04% | 59.26% | 85.19% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 18 | 50000 | 4055.15 | 2012-12-12 | 2012-12-26 | 10 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
0 | 19 | 25000 | 2990.4306 | 2012-12-26 | 2013-02-20 | 43 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13.95% | 30.23% | 44.19% | 58.14% | 100% | 100% | 100%

## Data
Bill_Item | time | Commodity_ID | WBS_Code | Planned_Quantity | Planned_Budget | Actual_Quantity | Actual_Budget | Planned_Progress_Spread | Planned_Hours_Spread | Planned_Quantity_Spread | Actual_Progress_Spread | Earned_Hours_Spread | Actual_Quantity_Spread | Actual_Hours_Spread
1 | 2012-01-06 | 0 | Baseline.06.02.01.01.01 | 253 | 1514.9701 | 253 | 1514.9701 | 0% | 0 | 0 | 0% | 0 | 0 | #DIV/0!

## Cover & Definition
WORKBOOK CONTENTS
PROJECT INFORMATION
[6 empty] | Worksheet Name | Worksheet Description
| Project Name: | Sample Project |  |  |  | Cover & Defination | This worksheet
[6 empty] | WBS | WBS
| Project No.: | 2564 | Period No.: | 3 |  | Commodity | Commodities
| Data Date: | 2012-01-20 |  |  |  | Baseline | Baseline Dates.
[6 empty] | Holiday | Holidays
[6 empty] | Period | Period definition
[6 empty] | BOQ | Bill of Quantity Data
[6 empty] | Data | internal Datasets, do not modify
BASELINE INFORMATION | [5 empty] | Spent Hours | Spent Hours
| Revision No: | 0 |  |  |  | Actual Progress | Weekly Actual Physical Progress
[6 empty] | Dashboard | Progress S curve, Tabular report
| Data Date: | 2012-01-01

## Tabular_Report_Quantity (hidden)
Installed Quantities
Commodity_ID | Commodity | Budget Total QTY | Quantity At Completion | Installed to Date | Percent complet | Planning this Week | Actual this week | Remaining work
CW | Foundation Civil Works | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0
MC1 | EREC.OF ASSEMBLED MACHINERY | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0
FC | FIN.COAT FOR MACH./MEC.LIFTING | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0
TS | Top soil removal | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0
GE | GENERAL EXCAVATIONS | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0
GB | General backfil. of area/roads | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0

## Tabular_Report_Progress (hidden)
Project Progress
| WBS | Budget Hours | Current Hours | Weight | Current Week % |  | Cumul %
L2 |  |  |  |  | Planned | Actual | Planned | Actual
Baseline.06 | CONSTRUCTION | 0 | 0 | #DIV/0! | NA | NA | NA | NA | 0
Baseline.06.01 | GENERAL | 0 | 0 | #DIV/0! | NA | NA | NA | NA | 0
Baseline.06.02 | PROCESS | 0 | 0 | #DIV/0! | NA | NA | NA | NA | 0
Baseline.06.03 | UTILITIES | 0 | 0 | #DIV/0! | NA | NA | NA | NA | 0
Baseline.06.04 | TANK FARM | 0 | 0 | #DIV/0! | NA | NA | NA | NA | 0
| Actual is Based on | Current

## CPI (hidden)
Period | Earned | Actual | Productivity
2012-01-06 | 0 | #REF! | #N/A
2012-01-13 | 0 | #REF! | #N/A
2012-01-20 | 0 | #REF! | #N/A
2012-01-27 | 0 | #REF! | #N/A
2012-02-03 | 0 | #REF! | #N/A
2012-02-10 | 0 | #REF! | #N/A
2012-02-17 | 0 | #REF! | #N/A
2012-02-24 | 0 | #REF! | #N/A
2012-03-02 | 0 | #REF! | #N/A
2012-03-09 | 0 | #REF! | #N/A
2012-03-16 | 0 | #REF! | #N/A
2012-03-23 | 0 | #REF! | #N/A
2012-03-30 | 0 | #REF! | #N/A
2012-04-06 | 0 | #REF! | #N/A
2012-04-13 | 0 | #REF! | #N/A
2012-04-20 | 0 | #REF! | #N/A
2012-04-27 | 0 | #REF! | #N/A
2012-05-04 | 0 | #REF! | #N/A
2012-05-11 | 0 | #REF! | #N/A
2012-05-18 | 0 | #REF! | #N/A
2012-05-25 | 0 | #REF! | #N/A
2012-06-01 | 0 | #REF! | #N/A
2012-06-08 | 0 | #REF! | #N/A
2012-06-15 | 0 | #REF! | #N/A
2012-06-22 | 0 | #REF! | #N/A
2012-06-29 | 0 | #REF! | #N/A
2012-07-06 | 0 | #REF! | #N/A
2012-07-13 | 0 | #REF! | #N/A
2012-07-20 | 0 | #REF! | #N/A
2012-07-27 | 0 | #REF! | #N/A
2012-08-03 | 0 | #REF! | #N/A
2012-08-10 | 0 | #REF! | #N/A
2012-08-17 | 0 | #REF! | #N/A
2012-08-24 | 0 | #REF! | #N/A
2012-08-31 | 0 | #REF! | #N/A
2012-09-07 | 0 | #REF! | #N/A
2012-09-14 | 0 | #REF! | #N/A
2012-09-21 | 0 | #REF! | #N/A
2012-09-28 | 0 | #REF! | #N/A
2012-10-05 | 0 | #REF! | #N/A
2012-10-12 | 0 | #REF! | #N/A
2012-10-19 | 0 | #REF! | #N/A
2012-10-26 | 0 | #REF! | #N/A
2012-11-02 | 0 | #REF! | #N/A
2012-11-09 | 0 | #REF! | #N/A
2012-11-16 | 0 | #REF! | #N/A
2012-11-23 | 0 | #REF! | #N/A
2012-11-30 | 0 | #REF! | #N/A
2012-12-07 | 0 | #REF! | #N/A
2012-12-14 | 0 | #REF! | #N/A
2012-12-21 | 0 | #REF! | #N/A
2012-12-28 | 0 | #REF! | #N/A
2013-01-04 | 0 | #REF! | #N/A
2013-01-11 | 0 | #REF! | #N/A
2013-01-18 | 0 | #REF! | #N/A
2013-01-25 | 0 | #REF! | #N/A
2013-02-01 | 0 | #REF! | #N/A
2013-02-08 | 0 | #REF! | #N/A
2013-02-15 | 0 | #REF! | #N/A
2013-02-22 | 0 | #REF! | #N/A